## Copy of Gantt Chart
GANTT CHART TEMPLATE | [6 empty] | Smartsheet Tip ➜ | [5 empty] | A Gantt chart's visual timeline allows you to see details about each task as well as project dependencies.
PROJECT TITLE |  | Real Time Bare Skinned Images Filtering using CNN |  |  |  |  | COMPANY NAME | [6 empty] | A.P Shah Institute of Technology
PROJECT GUIDE |  | Prof.Jaya Gupta |  |  |  |  | DATE | [6 empty] | 2019-08-27
WBS NUMBER | TASK TITLE | TASK OWNER | START DATE | DUE DATE | DURATION(Weeks) | PCT OF TASK COMPLETE | PHASE ONE | [14 empty] | PHASE TWO | [14 empty] | PHASE THREE | [14 empty] | PHASE FOUR
[7 empty] | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12
[7 empty] | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
1 | Project Conception and Initiation
1.1 | Research paper search | Pratik,Tina,Kshitija | 2019-07-10 | 2019-07-26 | 3 | 100% | bar: WEEK 1 W to WEEK 1 F; WEEK 5 T
1.1.1 | Research paper finalization | Pratik,Tina,Kshitija | 2019-07-10 | 2019-07-26 | 3 | 100% | bar: WEEK 2 T to WEEK 2 W; WEEK 5 T
1.2 | Project Title | Pratik,Tina,Kshitija | 2019-07-10 | 2019-07-26 | 3 | 100% | bar: WEEK 2 R; WEEK 3 M; WEEK 5 T
1.3 | Abstract | Pratik | 2019-08-23 | 2019-08-30 | 1 | 100% | bar: WEEK 4 M to WEEK 4 T; WEEK 5 T
1.4 | Objectives | Pratik | 2019-08-23 | 2019-08-30 | 1 | 100% | bar: WEEK 4 W; WEEK 5 T
1.5 | Literature Review | Pratik | 2019-08-23 | 2019-08-30 | 1 | 100% | bar: WEEK 4 W; WEEK 5 T
1.6 | Problem Definition | Kshitija | 2018-03-23 | 2019-08-30 | 1 | 100% | bar: WEEK 4 T; WEEK 5 T
1.7 | Scope | Kshtiija | 2019-08-23 | 2019-08-30 | 1 | 100% | bar: WEEK 4 T; WEEK 5 T
1.8 | Technology stack | Tina | 2019-08-23 | 2019-08-30 | 1 | 50% | bar: WEEK 4 W to WEEK 4 F; WEEK 5 T
1.9 | Benefits for environment |  | 2019-08-23 | 2019-08-30 | 1 | 0% | bar: WEEK 5 T
1.1 | Benefits for society | Kshitija | 2019-08-23 | 2019-08-30 | 1 | 100% | bar: WEEK 4 W; WEEK 5 T
1.11 | Applications | Kshitija | 2019-08-23 | 2019-08-30 | 1 | 100% | bar: WEEK 4 W; WEEK 5 T
2 | Project Design
2.1 | Proposed System | Tina | 2019-09-19 | 2019-09-27 | 1 | 70% | bar: WEEK 5 M to WEEK 5 T
2.2 | Design(Flow Of Modules) | Tina | 2019-09-19 | 2019-09-27 | 1 | 70% | bar: WEEK 5 T
2.3 | Activity Diagram | Pratik,Kshitija | 2019-09-19 | 2019-09-27 | 1 | 40% | bar: WEEK 5 T to WEEK 5 R
2.4 | Use Case Diagram | Pratik,Kshitija | 2019-09-19 | 2019-09-27 | 1 | 40% | bar: WEEK 5 T to WEEK 5 W
2.5 | Description Of Use Case | Pratik | 2019-09-19 | 2019-09-27 | 1 | 50% | bar: WEEK 5 T to WEEK 5 W
2.6 | Modules | Pratik,Tina,Kshitija | 2019-09-19 | 2019-09-27 | 1 | 100% | bar: WEEK 5 T
2.6.1 | Module-1 | Pratik,Tina,Kshitija | 2019-09-19 | 2019-09-27 | 1 | 100% | bar: WEEK 5 T
2.6.2 | Module-2 | Pratik,Tina,Kshitija | 2019-09-19 | 2019-09-27 | 1 | 100% | bar: WEEK 5 T
2.6.3 | Module-3 | Pratik,Tina,Kshitija | 2019-09-19 | 2019-09-27 | 1 | 100% | bar: WEEK 5 T
2.6.4 | Module-4 |  |  |  |  | 0% | bar: WEEK 5 T
2.7 | Preparation Of Report | Pratik,Tina,Kshitija | 2019-09-19 | 2019-09-27 | 1 | 65% | bar: WEEK 5 T
3 | Project Implementation
3.1 | Module-1 | X |  |  | 0 | 100% | bar: WEEK 4 M; WEEK 4 W to WEEK 4 F; WEEK 5 T; WEEK 5 F to WEEK 6 W; WEEK 6 F to WEEK 7 T; WEEK 7 F; WEEK 9 M; WEEK 9 R to WEEK 9 F
3.2 | Module-2 | Y |  |  | 0 | 100% | bar: WEEK 5 T to WEEK 5 R; WEEK 6 T; WEEK 6 F; WEEK 7 T; WEEK 7 F to WEEK 8 W; WEEK 8 F; WEEK 9 F
3.3 | Module-3 | Y |  |  | 0 | 30% | bar: WEEK 7 F; WEEK 9 M to WEEK 9 T; WEEK 9 R to WEEK 9 F
3.4 | Module-4 | Z |  |  | 0 | 0% | bar: WEEK 5 T
4 | Testing
4.1 | Design of Test Cases | Y |  |  | 0 | 0% | bar: WEEK 5 T
4.2 | Testing | Y |  |  | 0 | 0% | bar: WEEK 5 T
5 | Results and Analysis
5.1 | Analysis Of Results | Y |  |  | 0 | 0% | bar: WEEK 5 T
5.2 | Graphical Representation | Y |  |  | 0 | 0% | bar: WEEK 5 T
5.3 | Report Preparation